## Project Schedule
[Project Name] – Project Schedule Plan
Activity Name | Progress % | Status | Start Date | End Date
PHASE 1: INITIATING
▸ Project Initiation | 0% | To Be Started | 2026-06-28 | 2026-07-04
Develop Project Charter | 0% | To Be Started | 2026-06-28 | 2026-06-29
Identify stakeholders | 0% | To Be Started | 2026-06-30 | 2026-07-01
Conduct kickoff meeting | 0% | To Be Started | 2026-07-02 | 2026-07-03
📄 Approved Project Charter | 0% | To Be Started | 2026-07-04 | 2026-07-04
▸ Procurement | 0% | To Be Started | 2026-07-05 | 2026-07-09
Define scope of work | 0% | To Be Started | 2026-07-05 | 2026-07-06
Prepare and internally approve RFP document | 0% | To Be Started | 2026-07-07 | 2026-07-08
📄 Approved RFP Document | 0% | To Be Started | 2026-07-09 | 2026-07-09
Issue RFP to eligible management consulting firms | 0% | To Be Started | 2026-07-10 | 2026-07-11
Receive vendor Q&A and issue clarifications | 0% | To Be Started | 2026-07-12 | 2026-07-13
Evaluate Technical/Financial proposals | 0% | To Be Started | 2026-07-15 | 2026-07-16
📄 Technical & Financial Evaluation Report | 0% | To Be Started | 2026-07-17 | 2026-07-17
Vendor Award Notice | 0% | To Be Started | 2026-07-18 | 2026-07-19
Sign contract and issue purchase order | 0% | To Be Started | 2026-07-20 | 2026-07-21
📄 Signed Contract & Purchase Order | 0% | To Be Started | 2026-07-22 | 2026-07-22
PHASE 2: PLANNING
▸ Project Planning | 0% | To Be Started | 2026-07-23 | 2026-07-30
Develop detailed project schedule | 0% | To Be Started | 2026-07-23 | 2026-07-24
Define scope, deliverables and WBS | 0% | To Be Started | 2026-07-25 | 2026-07-26
Develop resource plan | 0% | To Be Started | 2026-07-27 | 2026-07-28
Develop risk and communication plans | 0% | To Be Started | 2026-07-29 | 2026-07-30
📄 Approved Project Management Plan | 0% | To Be Started | 2026-07-31 | 2026-07-31
PHASE 3: EXECUTING
▸ Project Execution | 0% | To Be Started | 2026-08-01 | 2026-08-08
Execute project activities | 0% | To Be Started | 2026-08-01 | 2026-08-02
Monitor and control progress | 0% | To Be Started | 2026-08-03 | 2026-08-04
Manage risks, issues and changes | 0% | To Be Started | 2026-08-05 | 2026-08-06
Conduct status reporting | 0% | To Be Started | 2026-08-07 | 2026-08-08
📄 Major Deliverable Completed | 0% | To Be Started | 2026-08-09 | 2026-08-09
PHASE 4: CLOSING
▸ Project Closure | 0% | To Be Started | 2026-08-10 | 2026-08-13
Obtain stakeholders formal sign-off / COC | 0% | To Be Started | 2026-08-10 | 2026-08-11
Compile all project documentation and upload to the PMO Tracking tool | 0% | To Be Started | 2026-08-12 | 2026-08-13
📄 Project Closure | 0% | To Be Started | 2026-08-14 | 2026-08-14